## Sheet1
REU Summer 2018 Internship
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Priorities |  | 2018-06-11 | 2018-06-18 | 2018-06-25 | 2018-07-02 | 2018-07-09 | 2018-07-16 | 2018-07-23 | 2018-07-30 | 2018-08-06 | 2018-08-13
| Poster | 2018-06-25: Story-board Poster w/mentors [mock draft on paper]; 2018-07-02: J o e O u t O f T o w n; 2018-07-23: Poster draft to mentors (7/28); 2018-07-30: Poster draft to CSNE (8/01); 2018-08-06: Poster final to CSNE (8/08)
| Presentation (5 minutes) | 2018-08-06: Practice Presentation with the Lab (8/07)
1. Disseminate 2017-2018 designs
GOAL: Design format for presenting designs (final concept and ideas/prototyping)
How have others organized similar information? Tips: Take notes, screenshots, etc. as you go and build your powerpoint slidedeck | bar: 2018-06-11 to 2018-06-18
What information should be posted for each team? Tips: Dive into Google Drive for VIP/Club team projects to evaluate content and contact if more is needed | bar: 2018-06-18 to 2018-06-25
Design Layout - How do you envision a user finding and interacting with the posted information? | bar: 2018-06-25
| First Milestone ¦ Summary Presentation | 2018-06-25: (6/27)
Next Steps:
Incorporate Feedback & Document final concept | bar: 2018-07-09 to 2018-07-16
Compile organized information & files for each team | bar: 2018-07-09 to 2018-07-16
2. Identify design challenges for 2018-2019
GOAL: List of projects for HuskyADAPT club (smaller in scope) and VIP course
| How could the survey on HuskyADAPT website be improved? | 2018-06-11: Current state - what needs to improve?; 2018-06-18: Setup meeting w/Heather for Survey design
What should be added to the website to make the survey easier to find and more descriptive | bar: 2018-06-18
| First Milestone ¦ PowerPoint of your plan for the survey | 2018-06-25: (6/29)
Improve survey and test with lab | bar: 2018-07-09
Next Steps:
Design challenge template (1-page summary of each design challenge) | bar: 2018-07-16
Send out survey to community members | bar: 2018-07-16
Create interview document in preparation for meeting with groups who have design challenges (including proper expectations) | bar: 2018-07-16
Meet with groups [ongoing] | bar: 2018-07-23 to 2018-08-13
[ongoing] Input each challenge into 1-pg template [based on your opinion, begin organizing challenges into club/VIP] | bar: 2018-07-23 to 2018-08-13
3. Push forward a design challenge
As you go through the previous project materials, is there any project or a piece of a project you would like to purse? | bar: 2018-06-11 to 2018-06-18
Needs to be a project small in scope so you can complete over the summer, or prepare it for a VIP/club team | bar: 2018-06-11 to 2018-06-18
Reach out to deisgn team about a meeting - continue to familiarize myself with their work | bar: 2018-06-25
Based off information from meeting draft prototype | bar: 2018-07-09 to 2018-07-30
Test Prototype with need expert; make necessary improvements | bar: 2018-08-06
4. Help develop HuskyADAPT design workbook
GOAL: Improve structure for club and VIP teams. Design workbook will include activities and milestones for each team to work through.
Any examples found online?
Document/Keep a list of neat design resources or workbooks you come across
| Meet with Dr. Steele and Dr. Caspi to discuss in more detail and outline workbook | 2018-07-16: Meeting TBD
5. Personal Goals
Utilize HTML with the creation of the website | bar: 2018-07-02
Familiarize myself with HTML | bar: 2018-06-25 to 2018-07-09
Create the site using HTML | bar: 2018-07-02 to 2018-07-16
Utilize Java to push forward the Design Challenge | bar: 2018-07-02
Familiarize myself with Java | bar: 2018-06-25 to 2018-08-13
Create the Prototype using provided Java Script and edit to remap the keyboard | bar: 2018-07-02 to 2018-08-13